## Product Backlog
Product Name: | Robo Shop
Team ID: | 1
Name: | Pavanaj Biyani
Initials: | PB
Student ID: | 1001236871
(Additional names for teams only)
Name: | Kartik Gupta
Initials: | KG
Student ID: | 1001228675
Name: | Shweta Shikarkhane
Initials: | SS
Student ID: | 1001192846
Name: | Winston Starling
Initials: | WS
Student ID: | 1001346251
Total Features | 36 | Status | Sprint Ends
Sprint 1 Left | 30 | Completed | 2016-10-06
Sprint 2 Left | 26 | Completed | 2016-10-13
Sprint 3 Left | 25 | Completed | 2016-10-20
Sprint 4 Left | 24 | Completed | 2016-10-27
Sprint 5 Left | 24 | Completed | 2016-11-03
Sprint 6 Left | 24 | Completed | 2016-11-10
Sprint 7 Left | 24 | Due | 2016-11-17
Sprint 8 Left | 24 | Due | 2016-11-22
Feature ID | Prio | Status | Sprint # | Team Size | As a... | I want to... | So that... | Notes
1 | 1 | Completed | 5 | 1 | All | open a GUI main window | I can interact with RRS Manager with my mouse | No menu required here – run program, create a part
2 | 2 | Completed | 1 | 1 | PM | create robot parts | I can define robot models | No menu required here – run program, create a part
3 | 3 |  |  | 1 | PM | create robot parts via GUI dialogs | I can define robot models | An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
4 | 4 | Completed | 1 | 1 | PM | define new robot models | RRS can sell them to our Beloved Customers | Menu needed – create parts, then create a robot model
5 | 5 | Completed | 6 | 1 | PM | define new robot models via GUI dialogs | RRS can sell them to our Beloved Customers | Similar to robot parts (perhaps Create > Robot Model)
6 | 6 | Completed | 1 | 1 | BC | browse a catalog of robots | I can buy one or more robots | Need to list robots models, then list parts in selected model
7 | 7 |  |  | 1 | BC | browse a catalog of robots via a GUI report | I can buy one or more robots | A text output is OK initially, but an attractive HTML-like output is desired (perhaps (Report > All Robot Models)
8 | 8 |  |  | 1 | BC | see pictures of the robots in the GUI catalog | I can see what I'm buying | Add picture when defining robot model, and show it in the robot model report
9 | 9 | Completed | 1 | 1 | SA | create a robot order for a Customer | I can sell robots and thus do my job well | Select robot model and quantity, show details with total price
10 | 10 |  |  | 1 | PB | Create a new Beloved Customer via GUI | I can keep track of who's buying our products | The usual name, address, phone number, and email address (perhaps Create > Customer)
11 | 11 |  |  | 1 | PB | Create a new Sales Associate via GUI | I can keep track of my employees' performance | Name and employee number at a minimum (perhaps Create > Sales Associate)
12 | 12 | Completed | 6 | 1 | SA | Create a robot order for a Customer via GUI | I can sell robots and thus do my job well
13 | 13 | Completed | 3 | 2 | PB | ensure persistence of the RRS data | we don't lose orders or historical data | Write the data to the default filename and reload it next time the program runs
14 | 14 |  |  | 2 | PB | allow the users to save data explicitly via GUI | we can save data without exiting the program | Write the data to the default filename on command (perhaps File > Save to the default filename)
15 | 15 |  |  | 2 | PB | allow the users to load data explicitly via GUI | we can manage multiple stores in different files | Read the data from a user-selected file on command (perhaps File > Open)
16 | 16 |  |  | 2 | PB | allow the users to save data to a specified name via GUI | we can manage multiple stores in different files | Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
17 | 23 | Completed | 2 | 2 | PB / SA | view a list of orders per SA | I can estimate the value of employees / I can justify a raise | Show list of orders for an SA with total price, then list details of selected order
18 | 24 | Completed | 6 | 2 | PB / SA | view a report of orders per SA in the GUI | I can estimate the value of employees / I can justify a raise | A basic text report is fine (perhaps Report > Orders by Sales Associate)
19 | 17 |  |  | 3 | All | enable basic login by role and customize the GUI | we don't have options that don't apply to our roles | User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
20 | 18 |  |  | 3 | All | enable copy and paste from text fields | we can save typing | Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported
23 | 21 | Completed | 2 | 3 | BC | view my bill | I can pay for my robots | Show a BC invoice. Actual payment is outside the scope of this project
24 | 22 |  |  | 3 | BC | view my bill (invoice) in the GUI | I can pay for my robots | A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
25 | 25 | Completed | 2 | 3 | BC | view my orders | see what I have coming to me | Show list of orders for a BC with total price, then list details of selected order
26 | 26 |  |  | 3 | BC | view my orders in the GUI | see what I have coming to me | A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
27 | 27 | Completed | 2 | 4 | SA | view a sales report | I can justify a raise | Show list of orders for an SA with total price, then list details of selected order
28 | 28 | Completed | 6 | 4 | SA | view a sales report in the GUI | I can justify a raise | A basic text report is fine (perhaps Report > Orders by Sales Associate)
29 | 19 | Completed | 3 | 4 | PB | view a list of orders | I can manage the company | Show list of every order with total price, then list details of selected order
30 | 20 | Completed | 6 | 4 | PB | view a report of all orders in the GUI | I can manage the company | A basic text report is fine (perhaps Report > All Orders)
31 | 29 |  |  | 4 | All | Add multi-level undo | Worry less about making mistakes | This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
32 | 30 |  |  | 4 | BC | see a pie chart of a model's component costs | I can decide if I want a different model | Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
33 | 31 |  |  | Bonus | SA | create a bulk (2+) order for Customer via GUI | avoid proliferation of orders and paperwork | Allow more than one robot model (with respective quantity) on a single order
34 | 32 |  |  | Bonus | PM | hide robot parts via GUI | obsolete parts aren't accidentally used | Mark robot parts as “obsolete” and don't allow adding them to new robot models
35 | 33 |  |  | Bonus | PM | hide robot models via GUI | obsolete robots aren't ordered | Mark robot models as “obsolete” and don't allow adding them to new orders
36 | 34 |  |  | Bonus | SA | save a draft order and return to it later via GUI | I can multi-task between indecisive customers | Save an order that hasn't been complete, and allow SA to resume work on it later
37 | 35 |  |  | Extreme Bonus | BC | browse and order robots over the web | I don't have to talk to the Sales Associates! | (Probably can't address until Homework #6)
38 | 36 |  |  | Extreme Bonus | PB | avoid any delays in the RRS web software | my SA team is at maximum productivity | This likely means using threads for key processes (Probably can't address until Homework #6)

## Sprint 4 Backlog
Sprint # | 4 |  |  | *** Example Only – Set up a tab for EACH SPRINT ***
Start on | 2016-10-21
End on | 2016-10-26
Demo on | 2016-10-27
Total Tasks | 2
Day 1 Left | 2
Day 2 Left | 2
Day 3 Left | 2
Day 4 Left | 2
Day 5 Left | 2
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Assigned To | Description | Status | Notes
|  | Planning | All | Team meeting to decide what needs to be done for this project | Done
|  | General | PB | Created Scrum sheet for Sprint 4 | Done

## Sprint 5 Backlog
Sprint # | 5
Start on | 2016-10-21
End on | 2016-10-26
Demo on | 2016-10-27
Total Tasks | 4
Day 1 Left | 4
Day 2 Left | 2
Day 3 Left | 2
Day 4 Left | 2
Day 5 Left | 2
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Assigned To | Description | Status | Notes
1 | 1 | Coding | PB & SS | Created the main GUI window | Done
2 | - | Coding | KG | Made changes to read and write functions | Done | Fixed bugs
3 | - | Coding | PB | Refactoring GUI.cpp | Done
4 | - | General | PB | Updated Scrum spreadsheet | Done

## Sprint 6 Backlog
Sprint # | 6
Start on | 2016-11-04
End on | 2016-11-09
Demo on | 2016-11-10
Total Tasks | 9
Day 1 Left | 8
Day 2 Left | 8
Day 3 Left | 6
Day 4 Left | 4
Day 5 Left | 2
Day 6 Left | 2
Day 7 Left | 0
Task ID | Feature ID | Category | Assigned To | Description | Status | Notes
1 | 5 | Coding | All | Created the interface for creating new robot parts | Done
2 | - | Coding | PB | Created the callback for storing the data entered for robot parts | Done
3 | - | Coding | PB | Refactoring Code and related data | DOne
4 | - |  | PB | updated Scrum spreadhseet | Done
5 | 12 | Coding | WS | Wrote SA Report Callback | Done
6 | 18 | Coding | WS | Wrote SA Orders Callback | Done
7 | 28 | Coding | WS | Wrote SA Bill Callback | Done
8 | 30 | Coding | SS | Wrote Boss Orders Callback | Done
9 | 30 | Coding | SS | Wrote Boss Profit Callback | Done